## Tasks
Epic No. | Epic | Task No. | Task | Assigned to | Status | Blockers | comments
1 | Data loading | 1 | Figure out how to load HDF5 data into HBase | Arul | Done
|  | 2 | Load the data on Amazon EC2 HBase instance | Arul | Done
|  | 3 | Load sample Data on everyone's machine | All | Done
|  | 4 | Load data with year column on the ec2 machine |  |  |  | If Pig can import data into Hbase successfully, write a simple python script that adds an year column to the Hbase table.
|  | 5 | Make the dataset get mounted on the ec2 instance on its own
|  | 6 | Run Hbase in Pseudo Distributed Mode on the EC2 machine |  |  |  | Do this after finishing task#11
|  | 8 | Hbase returns an error for long running queries | Arul | Pending. Not pursued | Not sure of what is happening. Probably the biggest problem now.
|  | 9 | Hbase Enable Remote access
|  | 10 | Export and Importing data into HBase from full dataset | Yogi
|  | 11 | Access Hbase from remote computer | All
|  | 12 | Change load_data_pyspark program to take table name as a parameter
2 | Dataset Preparation | 1 | Write Spark SQL queries to return artists who have more than 20 songs and Filter out the songs that belong to these artists. | Arul | Done
|  | 2 | Provide a list of song ID in for test and train datasets | Arul | Done
|  | 3 | Make sample and full data accessible to all | Arul | Done
|  | 4 | Write PIG program to create text file from Hbase | Yogi | Done
|  | 5 | Backup and Restore Hbase. Save dataset as snapshot | Yogi | In-progress | How difficult is running the Pig script on the full dataset? Is it worth the effort ? Should we run year program and load dataset in pseudo distributed mode?
|  | 6 | Normalize the data in Hbase(Update the database) | Arul
|  | 7 | Prepare data for naïve bayes to be applied | Arul
3 | Data Transformation | 1 | Figure out HBase Scala interface | Yogi | Done
|  | 2 | Retrieve the data from HBase | Yogi | Done
|  | 3 | Figure out which features to use for PCA | All | Done | 90 Features
|  | 4 | Set up dev enviornment for spark and scala on your machine | All | Done
4 | Apply PCA | 1 | Figure out how to use PCA in scala. | Ameya | Done
|  | 2 | Load an entire row using scala and convert it to a form that can be directly applied to the MLLib | Ameya | Done
|  | 3 | Study output of PCA for further usage | Ameya | Cancelled
|  | 4 | Test results difference between using 90 attributes of timbre as opposed to 12
| Apply Naive Bayes | 1 | Write skeleton program for applying naïve Bayes | Ameya
|  | 2 | Decide the output format. Should group both test and train dataset by year | Ameya

## Details
Epic.Task | Detail
4.1 | import org.apache.spark.mllib.linalg.Matrix import org.apache.spark.mllib.linalg.distributed.RowMatrix val mat: RowMatrix = ... // Compute the top 10 principal components. val pc: Matrix = mat.computePrincipalComponents(10) // Principal components are stored in a local dense matrix. // Project the rows to the linear space spanned by the top 10 principal components. val projected: RowMatrix = mat.multiply(pc)